## Policy Objectives
Project
Year |  | Team ID | Team
Sprint |  | Start | End
Asset | Value | Objective |  | Exposure

## Threat Model
Project
Year | 2022/2023 | Team ID |  |  |  | Team
Sprint |  | Start |  |  |  | End
Asset | Value | Spoofing | Tampering | Repudiation | Information disclosure | DOS | Elevation of privilege | Danger | Unreliability | Absence of Resilience | Exposure | Attack | Inherent Probability | Inherent Risk | Control | Cost | Feasibility | Residual Probability | Residual Impact | Residual Risk | DUBBI
Wallet | 200.000-500.000 | X |  |  | X |  | X |  |  |  | 20.000-60.000 | Authentication Abuse (114) | 15% | 3.000-9.000
|  | X | [8 empty] | 10.000-20.000 | Identity Spoofing (151) | 18% | 1.800-3.600 | [6 empty] | Come funziona effettivamente l'autenticazione tramite wallet? È solo uno scambio di chiavi?
[7 empty] | X |  |  |  | 10.000-20.000 | Privilege Escalation (233) | 8% | 800-1.600 | [6 empty] | dobbiamo considerare anche questo o si suppone che l'utente protegga il suo wallet da solo?
|  | X |  | X | X |  | X |  |  |  | 20.000-60.000 | Use of known domain credentials (560) | 12% | 1.600-7.200 | [6 empty] | solo Chiara è d’accordo
Smart contract | 10.000-50.000 | X | X | [7 empty] | 5.000-10.000 | Content Spoofing (148) | 12% | 600-1.200 | [6 empty] | Questa minaccia riguarda sia lo spoofing che il tampering, nell'analisi preliminare avevamo considerato solo il tampering.
[7 empty] | X |  |  |  | 5.000-10.000 | Privilege Escalation (233) | 10% | 500-1.000
Register | 50.000-200.000 | X | X | [7 empty] | 20.000-40.000 | Content Spoofing (148) | 15% | 3.000-6.0000
Transaction Result | 5.000-10.000 | X | X | [7 empty] | 1.000-2.500 | Content Spoofing (148) | 15% | 150-375
Smart Contract Location | 50.000-100.000 | X | X | [7 empty] | 10.000-20.000 | Content Spoofing (148) | 15% | 1.500-3.000
[5 empty] | X | [5 empty] | 5.000-10.000 | Sniffing (157) | 20% | 1.000-2.000
Smart Contract Method | 50.000-100.000 | X | X | [7 empty] | 25.000-50.000 | Content Spoofing (148) | 15% | 3.750-7.500
[5 empty] | X | [5 empty] | 10.000-25.000 | Sniffing (157) | 20% | 2.000-5.000
Deploy Transaction | 200.000-500.000 |  | X |  | X |  |  |  | X |  | 50.000-100.000 | AiTM (94) | 21% | 10.500-21.000
[6 empty] | X |  |  |  |  | 50.000-150.000 | Flooding(125) | 23% | 11.500-34.500
Update Shards' State | 250.000-500.000 |  | X |  | X |  |  |  | X |  | 50.000-100.000 | AiTM (94) | 21% | 10.500-21.000
[6 empty] | X |  |  |  |  | 80.000-150.000 | Flooding(125) | 23% | 18.400-34.500
[6 empty] | X |  |  |  |  | 80.000-150.000 | Sustained Client Engagement (227) | 18% | 14.400-27.000
Shards' Mapping | 300.000-500.000 | X | X | [7 empty] | 100.000-150.000 | Content Spoofing (148) | 15% | 15.000-22.500
Shard's Address | 300.000-500.000 | X | X | [7 empty] | 100.000-150.000 | Content Spoofing (148) | 15% | 15.000-22.500